## Sheet1
Task Sessions | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61
Analysis
Project Proposal
Feasibility Study
End User Survey
Project Plan
Requirements Specification
Design
UI Wireframes
Neural Net Design
Pseudocode & Class Design
Implementation
Frame and Panel
Neural Net and Evolution setup
Main Menu
Fast Generation
Slow Generation
Average Survival Graph
Creature Cannabalism
Creature Names
Ongoing Research |  |  | d
Testing
Component & Integrative Testing
Frame and Panel
Test Plan
Neural Net
Main Menu
Slow Generation
Fast Generation
Average Food Graph
Creature Cannibalism
Creature Names
Functionality Testing
Beta Testing
Regression testing
Hollistic Testing
Evaluation
Efficiency
Effectiveness
Reliability
Robustness
Extra Implementation*
Highest and Lowest Survival Time graph
Sprites and backgrounds
Extra Testing*
Test Plan update
Highest and Lowest food graph
Observe generation after completion
Sprites and backgrounds integration
Extra Evaluation*
Efficiency
Effectiveness
Reliability
Robustness
* Will be done after project completion if time remains