## Sheet1
Task Sessions | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61
Analysis
Project Proposal
Feasibility Study
End User Survey
Project Plan
Requirements Specification
Design
UI Wireframes
Neural Net Design
Pseudocode & Class Design
Implementation
Frame and Panel
Neural Net and Evolution setup
Main Menu
Slow Generation
Fast Generation
Average Survival Graph
Creature Cannabalism
Creature Names
Ongoing Research
Testing
Component & Integrative Testing
Frame and Panel
Test Plan
Neural Net
Main Menu | [23 empty] | 2019
Slow Generation
Fast Generation
Average Food Graph
Creature Cannibalism
Creature Names
Functionality Testing
Beta Testing
Regression testing
Hollistic Testing
Evaluation
Efficiency
Effectiveness
Reliability
Robustness
Extra Implementation*
Highest and Lowest Survival Time graph
Sprites and backgrounds
Extra Testing*
Test Plan update
Highest and Lowest food graph
Observe generation after completion
Sprites and backgrounds integration
Extra Evaluation*
Efficiency
Effectiveness
Reliability
Robustness
* Will be done after project completion if time remains